## Backlog
User Story | Category | Description | Priority Level | Original Estimate (hrs) | Time Spent (hrs) | Updated Estimate (hrs) | Time Left (hrs) | Date Added | Date Assigned | Date Finished | Time Discrepancy
All | Summary | Sum of All Backlog | x | 194.5 | 7.5 | 194.5 | 187
Get Mac Working | Infrastructure | Get MacBook working by going to Apple Store | 1 | 3 | 3 | 3 | 0 | 2014-12-20
Update Xcode | Infrastructure | Update Xcode by running it | 1 | 0.5 | 0.5 | 0.5 | 0 | 2014-12-20
Create Initial App/Project | Project Setup | Create initial app in xcode | 1 | 1 | 1 | 1 | 0 | 2014-12-20
Learn Xcode | On-Boarding | Finish ToDoList Tutorial | 1 | 3 | 3 | 3 | 0 | 2014-01-09
Build Static Inbox ListView | Front-End - Inbox | Create a listView of Inbox with menu on top, has static data | 2 | 3 | 0 | 3 | 3 | 2014-12-20
Build Static Contact Page | Front-End - Contact | Create a view of contact pages, text mutable | 2 | 3 | 0 | 3 | 3 | 2014-12-20
Build Static Contact Log | Front-End - Log | Create a view with grid and add new entry button, fill with static data | 2 | 3 | 0 | 3 | 3 | 2014-12-20
Build Static Log Entry Page | Front-End - Log | Create a view with editable fields date and description | 2 | 2 | 0 | 2 | 2 | 2014-12-20
Create Archived/Snoozed Views | Front-End - Inbox | Copy Inbox ListView, modify slightly (at least data) | 3 | 2 | 0 | 2 | 2 | 2014-12-20
Create SQL DBs and Tables | Backend - DBs | Design and Create Tables for Contacts, Encounter Entries | 3 | 5 | 0 | 5 | 5 | 2014-12-20
Inboxes display dynamic data | Backend - Inbox | Link data from DB to front-end and filter according to inbox | 3 | 4 | 0 | 4 | 4 | 2014-12-20
Inboxes have linked navbar | Front-End - Inbox | Can switch views in inboxes, add new contact or manage tags via navmenu | 3 | 5 | 0 | 5 | 5 | 2014-12-20
Basic Swipe on InboxContacts | Front-End - Inbox | Swiping right sends to future (default amount of time, no prompt) Left to archive | 3 | 10 | 0 | 10 | 10 | 2014-12-20
Basic Swipe on Snoozed | Front-End - Inbox | Swiping left sends to inbox (default amount of time, no prompt) right to re-snooze | 3 | 10 | 0 | 10 | 10 | 2014-12-20
Basic Swipe on Archived | Front-End - Inbox | Swiping right sends to inbox (default amount of time, no prompt) Left to delete | 3 | 10 | 0 | 10 | 10 | 2014-12-20
Contact Page Navbar Linked | Front-End - Contact | Navbar takes user to log or back to whatever previous view | 3 | 4 | 0 | 4 | 4 | 2014-12-20
Contact Log Navbar Linked | Front-End - Log | Navbar takes users to contact page or back to previous view | 3 | 4 | 0 | 4 | 4 | 2014-12-20
New Day sends snoozed to inbox | Backend - Log | New day triggers event and all contacts that are snoozed till that day to go to inbox | 3 | 10 | 0 | 10 | 10 | 2014-12-20
Create Manage Tags Menu | Front-End - Tags | Create a menu for filtering by tags/managing default snoozes | 4 | 7 | 0 | 7 | 7 | 2014-12-20
Add Search bar | Front-End - Inbox | Create a search bar at top of list of contacts in the three inboxes | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Dynamic Filtering in Inboxes | Backend - Inbox | Allow searching (by name/tag) for all three inboxes and filters in real-time | 4 | 5 | 0 | 5 | 5 | 2014-12-20
Contact Page Has Dynamic Data | Backend - Contact | Link DB with contact frontend and displays correct info | 4 | 4 | 0 | 4 | 4 | 2014-12-20
Contact Log Has Dynamic Data | Backend - Log | Link DB with log and display dynamic data based on person and entries (sorted) | 4 | 4 | 0 | 4 | 4 | 2014-12-20
Log Entry Has Dynamic Data | Backend - Log | Link DB with log entry page and display correct data | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Log Entry Page has full CRUD | Backend - Log | Leaving Log Entry Page updates database accordingly, add a delete entry button | 4 | 5.5 | 0 | 5.5 | 5.5 | 2014-12-20
Tap Row Entry in Log to Access | Front-End - Log | Tapping a row in encounters log opens that entry for editing/viewing | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Tap Row in Inboxes to Access | Front-End - Inbox | Tapping a row (contact) in inboxes opens info on that contact | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Contacts List Displays Contact Gist | Front-End - Inbox | Each Row contains the right info on the user (have to create rowEntryView) | 4 | 6 | 0 | 6 | 6 | 2014-12-20
Inbox Contacts ordered correctly | Front-End - Inbox | Inbox - Date Added to Inbox: old->new, Archive - A->Z, Snoozed: Snooze End first->last | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Contact Editing Page has full CRUD | Backend - Contact | Leaving Contact Editing Page updates corresponding info in DB | 4 | 5.5 | 0 | 5.5 | 5.5 | 2014-12-20
Log Actions into Database | Front-End - Backend | Log all actions (user and app) into database | 4 | 10 | 0 | 10 | 10 | 2014-12-23
Contact Log contains search bar | Front-End - Log | Self-explanatory add bar to top | 5 | 2 | 0 | 2 | 2 | 2014-12-20
Contact Log filters via search | Backend - Log | Log Entries filtered by description string matching (add new task for date range searching) | 5 | 3 | 0 | 3 | 3 | 2014-12-20
Advanced Swiping in Mailbox View | Front-End - Inbox | Different Swipe Lengths Have Different Actions | 5 | 15 | 0 | 15 | 15 | 2014-12-23
Multi-touch Capabilities | Front-End - Inbox | Can swipe multiple at once (different swipes at same time) | 5 | 15 | 0 | 15 | 15 | 2014-12-23
Shake to Undo | Front-End - Inbox | Shake to undo | 5 | 15 | 0 | 15 | 15 | 2014-12-23
sx | Summary | Entire Backlog Summary | n/a | 206.5 | 0 | 206.5 | 206.5 | 2014-12-20 | 2014-12-20

## Sprint 1
User Story | Category | Description | Priority Level | Original Estimate (hrs) | Time Spent (hrs) | Updated Estimate (hrs) | Time Left (hrs) | Date Added | Date Assigned | Date Finished | Time Discrepancy
All | Summary | Sum of All Backlog | x | 39.5 | 4.5 | 39.5 | 35
Get Mac Working | Infrastructure | Get MacBook working by going to Apple Store | 1 | 3 | 3 | 3 | 0 | 2014-12-20
Update Xcode | Infrastructure | Update Xcode by running it | 1 | 0.5 | 0.5 | 0.5 | 0 | 2014-12-20
Create Initial App/Project | Project Setup | Create initial app in xcode | 1 | 1 | 1 | 1 | 0 | 2014-12-20
Build Static Inbox ListView | Front-End - Inbox | Create a listView of Inbox with menu on top, has static data | 2 | 3 | 0 | 3 | 3 | 2014-12-20
Build Static Contact Page | Front-End - Contact | Create a view of contact pages, text mutable | 2 | 3 | 0 | 3 | 3 | 2014-12-20
Build Static Contact Log | Front-End - Log | Create a view with grid and add new entry button, fill with static data | 2 | 3 | 0 | 3 | 3 | 2014-12-20
Build Static Log Entry Page | Front-End - Log | Create a view with editable fields date and description | 2 | 2 | 0 | 2 | 2 | 2014-12-20
Create Archived/Snoozed Views | Front-End - Inbox | Copy Inbox ListView, modify slightly (at least data) | 3 | 2 | 0 | 2 | 2 | 2014-12-20
Create SQL DBs and Tables | Backend - DBs | Design and Create Tables for Contacts, Encounter Entries | 3 | 5 | 0 | 5 | 5 | 2014-12-20
Inboxes display dynamic data | Backend - Inbox | Link data from DB to front-end and filter according to inbox | 3 | 4 | 0 | 4 | 4 | 2014-12-20
Inboxes have linked navbar | Front-End - Inbox | Can switch views in inboxes, add new contact or manage tags via navmenu | 3 | 5 | 0 | 5 | 5 | 2014-12-20
Contact Page Navbar Linked | Front-End - Contact | Navbar takes user to log or back to whatever previous view | 3 | 4 | 0 | 4 | 4 | 2014-12-20
Contact Log Navbar Linked | Front-End - Log | Navbar takes users to contact page or back to previous view | 3 | 4 | 0 | 4 | 4 | 2014-12-20
sx | Summary | Entire Backlog Summary | n/a | 206.5 | 0 | 206.5 | 206.5 | 2014-12-20 | 2014-12-20

## Sprint 2
User Story | Category | Description | Priority Level | Original Estimate (hrs) | Time Spent (hrs) | Updated Estimate (hrs) | Time Left (hrs) | Date Added | Date Assigned | Date Finished | Time Discrepancy
All | Summary | Sum of All Backlog | x | 40 | 0 | 40 | 40
Basic Swipe on InboxContacts | Front-End - Inbox | Swiping right sends to future (default amount of time, no prompt) Left to archive | 3 | 10 | 0 | 10 | 10 | 2014-12-20
Basic Swipe on Snoozed | Front-End - Inbox | Swiping left sends to inbox (default amount of time, no prompt) right to re-snooze | 3 | 10 | 0 | 10 | 10 | 2014-12-20
Basic Swipe on Archived | Front-End - Inbox | Swiping right sends to inbox (default amount of time, no prompt) Left to delete | 3 | 10 | 0 | 10 | 10 | 2014-12-20
New Day sends snoozed to inbox | Backend - Log | New day triggers event and all contacts that are snoozed till that day to go to inbox | 3 | 10 | 0 | 10 | 10 | 2014-12-20
sx | Summary | Entire Backlog Summary | n/a | 206.5 | 0 | 206.5 | 206.5 | 2014-12-20 | 2014-12-20

## Sprint 3
User Story | Category | Description | Priority Level | Original Estimate (hrs) | Time Spent (hrs) | Updated Estimate (hrs) | Time Left (hrs) | Date Added | Date Assigned | Date Finished | Time Discrepancy
All | Summary | Sum of All Backlog | x | 112 | 0 | 112 | 112
Create Manage Tags Menu | Front-End - Tags | Create a menu for filtering by tags/managing default snoozes | 4 | 7 | 0 | 7 | 7 | 2014-12-20
Add Search bar | Front-End - Inbox | Create a search bar at top of list of contacts in the three inboxes | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Dynamic Filtering in Inboxes | Backend - Inbox | Allow searching (by name/tag) for all three inboxes and filters in real-time | 4 | 5 | 0 | 5 | 5 | 2014-12-20
Contact Page Has Dynamic Data | Backend - Contact | Link DB with contact frontend and displays correct info | 4 | 4 | 0 | 4 | 4 | 2014-12-20
Contact Log Has Dynamic Data | Backend - Log | Link DB with log and display dynamic data based on person and entries (sorted) | 4 | 4 | 0 | 4 | 4 | 2014-12-20
Log Entry Has Dynamic Data | Backend - Log | Link DB with log entry page and display correct data | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Log Entry Page has full CRUD | Backend - Log | Leaving Log Entry Page updates database accordingly, add a delete entry button | 4 | 5.5 | 0 | 5.5 | 5.5 | 2014-12-20
Tap Row Entry in Log to Access | Front-End - Log | Tapping a row in encounters log opens that entry for editing/viewing | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Tap Row in Inboxes to Access | Front-End - Inbox | Tapping a row (contact) in inboxes opens info on that contact | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Contacts List Displays Contact Gist | Front-End - Inbox | Each Row contains the right info on the user (have to create rowEntryView) | 4 | 6 | 0 | 6 | 6 | 2014-12-20
Inbox Contacts ordered correctly | Front-End - Inbox | Inbox - Date Added to Inbox: old->new, Archive - A->Z, Snoozed: Snooze End first->last | 4 | 3 | 0 | 3 | 3 | 2014-12-20
Contact Editing Page has full CRUD | Backend - Contact | Leaving Contact Editing Page updates corresponding info in DB | 4 | 5.5 | 0 | 5.5 | 5.5 | 2014-12-20
Log Actions into Database | Front-End - Backend | Log all actions (user and app) into database | 4 | 10 | 0 | 10 | 10 | 2014-12-23
Contact Log contains search bar | Front-End - Log | Self-explanatory add bar to top | 5 | 2 | 0 | 2 | 2 | 2014-12-20
Contact Log filters via search | Backend - Log | Log Entries filtered by description string matching (add new task for date range searching) | 5 | 3 | 0 | 3 | 3 | 2014-12-20
Advanced Swiping in Mailbox View | Front-End - Inbox | Different Swipe Lengths Have Different Actions | 5 | 15 | 0 | 15 | 15 | 2014-12-23
Multi-touch Capabilities | Front-End - Inbox | Can swipe multiple at once (different swipes at same time) | 5 | 15 | 0 | 15 | 15 | 2014-12-23
Shake to Undo | Front-End - Inbox | Shake to undo | 5 | 15 | 0 | 15 | 15 | 2014-12-23